## Delovni list1
|  |  | 1st year |  |  |  | 2nd year |  |  |  | 3rd year |  |  |  | 4th year
| Quarter |  | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV
Research line 1 | WP1a | Imprecise probability trees
Joint models | WP1b | Joint probability model
basic properties | WP1c | Lower and upper bounds | bar: 1st year II to 2nd year II
Research line 2 | WP2a | Computing bounds | bar: 1st year I to 2nd year II
Computational | WP2b | Error estimation | bar: 1st year I to 1st year III
methods | WP2c | Perturbation analysis | bar: 3rd year I to 3rd year IV
| WP2d | Coefficients of ergodicity | bar: 2nd year II to 2nd year IV
Research line 3 | WP3a | Conditions for convergence | bar: 2nd year III to 3rd year II
Limit behaviour | WP3b | Computing limit distributions | bar: 3rd year I to 3rd year IV
| WP3c | Classification of states | bar: 3rd year III to 4th year II
Research line 4 | WP4a | Conceptual properties | bar: 2nd year III to 3rd year IV
Time reversal | WP4b | Reversible chains | bar: 3rd year I to 4th year III
WP4c
Research line 5 | WP5a
Applications | WP5b
WP5c
| G | Ghent
| L | Ljubljana
| B | Both